SSN/VMS synergies pilot project

Kick off meeting 	Rome 11 October 2011

Agenda item 4

Lisbon, 21 September 2011

Work plan

| Executive summary | This document presents the detailed work plan related to the operational phase. |
| --- | --- |
| Action to be taken | As per paragraph 3 |
| Related documents | - Minutes of Directors meeting (FR, IT, SP) on maritime surveillance pilot projects (Lisbon, 10 March 2010) - Minutes of SSN High Level Steering Group 5 on “SSN/VMS pilot project” |

1. INTRODUCTION

In order to define the detailed activity plan and the subsequent milestones related to the operational phase of the SSN/VMS pilot project, the work breakdown structure is proposed in Annex 1 of this paper.

2. PRELIMINARY ACTIVITIES

To facilitate the process of implementing the work plan, EMSA requested some preliminary information from participating countries to be provided by the 23 September 2011:

- A description of how the FMCs are connected, indicating the HTTPS method used (such as Get or Post or other). The definition of the method is necessary for EMSA to determine the technical communication between EMSA and FMCs when sending/receiving messages. To this end, EMSA asked some samples of the strings concerning both the position messages sent and received (meaning the full string that generally encapsulates the NAF position message);

- The details of fishing vessels provided with AIS (preferably 5) which would participate in the pilot project in order to populate the database used to get the correlation between the two data sources (VMS and AIS);

- The confirmation that the procedure for issuing the EMSA digital certificates has been activated. The certificate is needed to ensure the IT secure communication between EMSA and the FMC. EMSA Maritime Support Service is able to provide assistance to perform this procedure;

- The geographic polygons identifying the fishing zones under the responsibility of each FMC in order to define in the central system the sea areas associated to the participating countries.

- The contact details of the key people involved in the pilot project and information on whether the FMC has 24/7 capabilities. This information is useful for monitoring activities related to the pilot project.

Should a change occur that affects access for the SSN user (e.g. change of the IP address, change of office location, change to a post that does not require access to SSN, etc.), this should be notified to the EMSA MSS as soon as possible. This way, EMSA will be able to take the appropriate action to re-configure the relevant user account.

3. ACTIONS REQUIRED

Participating MSs are invited to take note of the above mentioned information. FMCs which not have yet provided the information under the paragraph 2 are kindly request to send the information to EMSA by the 28 October 2011.

# ANNEX 1

Work plan

| Activity |  | Tasks for FMCs | Tasks for EMSA | Milestone | Deadline |
| --- | --- | --- | --- | --- | --- |
| Preliminary activities | - To launch the procedure for issuing the digital certificates between SSN and FMCs | To follow the procedure in annex 2 and to provide to EMSA the A and B forms in annex 2 (to be provided both the client certificate and the server certificate for the 2-way SSL) | - To issue the Digital Certificates - To provide assistance to MSs to perform the task | EMSA and FMCs will install the proper Digital Certificates | End October 2011(*) (*) if not already done |
|  | - Assignment of the responsible Officer in the FMCs | To provide to EMSA the form C in annex 2 | - To provide assistance to MSs to perform the task | EMSA will take note of the responsible Officer’s details |  |
|  | - To provide the interface parameters | To provide to EMSA the information on how FMCs are connected indicating the HTTPS method used (Get, Post or other) | - To provide assistance to MSs to perform the task | EMSA will take note of the interface parameters |  |
|  | - To provide the list with the selected fishing vessels (F/Vs) fitted with VMS and AIS Class “A” (if available) and other technical information | To provide to EMSA the filled forms in annex 3 including the requested details for the selected F/Vs and other technical information | - To provide assistance to MSs to perform the task - To inject the F/Vs details in a specific DB in order to get the AIS/VMS correlation | Information stored in EMSA DB |  |
|  | - Definition of the geographic areas under the responsibility of the FMCs | To provide to EMSA a shapefile (if available) with the coordinates of the fishing areas under the FMC responsibility (annex 3) | - To inject the coordinates in the application | Information stored in the application |  |
|  | - Connection tests between EMSA and FMCs | Common task: to perform some tests between EMSA and MSs in order to check the quality and the reliability of the data exchange. |  | Execution of test data exchange between EMSA and FMCs and feedback |  |
| Periodic surveys |  | To provide to EMSA on a case-by-case basis feedback on the on-going project. To this end EMSA and FMCs may manage specific operational tests better described in the “monitoring & assessment” paper | To analyse the results provided by participating MSs | Provision of feedback from FMCs | T.B.D. |
| Final assessment |  | To provide to EMSA the final assessment sheet according to the “monitoring & assessment” paper | To analyse the results provided by participating MSs | Provision of the final assessment from FMCs | End April 2012 |
| Evaluation activities by EMSA |  | //// | To provide a final document in order to evaluate the outcomes of the pilot project | To submit to participating MSs the final report | End May 2012 |
| Final meeting |  | After the 6-month operational phase, a final meeting between EMSA and the participating countries will be arranged in order to discuss the outcomes of the project. In addition, the results will be presented to the HLSG and to the SSN workshop |  |  | T.B.D. |

ANNEX 2

Procedures for issuing digital certificates

- Confidentiality and 2-way SSL

Member States have adopted the 2-way SSL method (Secure Socket Layer) to ensure SSN data security. Digital certificates should be installed both at the system server hosted by EMSA as well as the site where the Vessel Monitoring System, hosted by the National Authorities, will be installed.

EMSA has created its own Certification Authority (CA) to issue the digital certificates used in the SSN communication process. To provide your Administration with the certificates you are kindly requested:

- To complete and send the “Appointment of the Officer Responsible for the Server” and the Certificate Registration Form (included in Appendix I and Appendix II).

- To generate the Certificate Signing Requests (CSR) for both client and server certificates (refer to http://www.openssl.org/ for general instructions or to https://www.geotrust.com/support/generate-csr/ for specific instructions depending on the server type).

- Digital certification procedure

The following procedure should be applied by your Administration for getting the VMS 2-way SSL server and client certificates:

- Open a call to the Maritime Support Services of EMSA (Tel: + 351 21 1209 415, Fax: +351 21 1209 480, Email: MaritimeSupportServices@emsa.europa.eu) requesting for the digital certificates for SSN-European Index Server (SSN-EIS).

- The MSS will request your Administration to complete the “Appointment of the Officer Responsible for the Server” (see appendix I), the Certificate Registration Form (see appendix II) and to send the Certificate Signing Request (CSR).

- Your Administration will send back to the MSS, by e-mail (signed documents have to be scanned into PDF files) the following documents, for both client and server certificates:

  - The Certificate Registration Form

  - The Appointment of the Officer Responsible for the Server

  - The CSR file

  - A legible photocopy of a valid identity card of the Officer signatory to the Registration in a) above (and appointed under b) above).

- After verification, the MSS will inform your Administration about the status of the application.

- EMSA will send the digital certificates to the email address of the Officer Responsible (i.e. the email that appears in the Registration Form). MSS will be available to support your Administration if any errors or defects are discovered in the certificate.

- Your Administration will install the digital certificates issued by EMSA only on the server corresponding to the dom6ain indicated on the said certificates (in the Common Name field).

- If problems occur during the procedure, your Administration may contact the MSS.

- Your Administration will inform the MSS once the task has been completed.

- Your Administration should follow the above mentioned procedure when the certificate renewal is due.

# Form A

# Certificate Registration Form (CLIENT CERTIFICATE)

(ATTENTION: to be filled-in per CSR)

| System | SSN-GI  VMS PROXY SSN-EIS LRIT SHIP DB EU LRIT DC: LRIT2ES EU LRIT DC: ES2LRIT THETIS CSN (select just one option of the above) |
| --- | --- |
| Environment | PRODUCTION TRAINING TEST DEVELOPMENT (select just one option of the above) |
| Type of certificate | Server certificate - Required for 1-way SSL communications in the following applications: EU LRIT DC: LRIT2ES, only in TEST environment - Required for 2-way SSL communications in the following applications: SSN-EIS, EU LRIT DC: LRIT2ES, VMS PROXY Client certificate - Required for 2-way SSL communications in the following applications: SSN-EIS, SSN-GI, LRIT SHIP DB, EU LRIT DC: ES2LRIT, THETIS, CSN, VMS PROXY (select just one option of the above) |
| Information about the Officer Responsible for the Server1 | Value |
| First Name |  |
| Last Name |  |
| E-mail 2 |  |
| Company Name |  |
| Registered Office Address |  |
| City/Town |  |
| Postal code |  |
| Province |  |
| Telephone |  |
| Fax |  |
| Requesting Organization Information | Value |
| Organization Name |  |
| Organization Unit 3 |  |
| Registered Office Address |  |
| City/Town |  |
| Postal code |  |
| Country |  |
| First Name of the Representative of the Organization4 |  |
| Last Name of the Representative of the Organization |  |
| E-mail of the Representative of the Organization5 |  |
| CSR Specific Information | Value |
| Common Name (CN) 6 |  |
| Revocation code 7 |  |
| Additional Information | Value |
| End-point 8 |  |
| Type of Server 9 |  |

1 The Officer Responsible for the Server is the operational reference person, authorized by the Representative of the Organization.

2 The electronic mailbox to which the Registration Form and the issued certificate are sent.

3 The Organization Unit of the web server is that which appears in the Organisational Unit (OU) in the subject field of the certificate.

4 The representative of the Organization is the person indicated by the appointment signed by the Legal Representative, or equivalent.

5 The electronic mailbox to which the Registration, which must be signed by the representative of the Organization or equivalent; the Appointment of the Officer Responsible for the Server and the issued certificate are sent.

6 The Fully Qualified Domain Name (FQDN) in case you are requesting a server certificate.

7 The revocation code is used to verify telephone requests. It consists of 9 numbers uniquely associated to the certificate requested.

8 The end-point is only needed for EU LRIT DC certificates (e.g.: https://es-evtest.member-state.eu/lrit2es, using SSL) and VMS PROXY certificates

9 The type of web server (IIS, ePlanet, Apache, etc.).

Place and date _______________________________

Signature of the Officer Responsible for the Server

# Form B

# Certificate Registration Form (SERVER CERTIFICATE)

(ATTENTION: to be filled-in per CSR)

| System | SSN-GI  VMS PROXY SSN-EIS LRIT SHIP DB EU LRIT DC: LRIT2ES EU LRIT DC: ES2LRIT THETIS CSN (select just one option of the above) |
| --- | --- |
| Environment | PRODUCTION TRAINING TEST DEVELOPMENT (select just one option of the above) |
| Type of certificate | Server certificate - Required for 1-way SSL communications in the following applications: EU LRIT DC: LRIT2ES, only in TEST environment - Required for 2-way SSL communications in the following applications: SSN-EIS, EU LRIT DC: LRIT2ES, VMS PROXY Client certificate - Required for 2-way SSL communications in the following applications: SSN-EIS, SSN-GI, LRIT SHIP DB, EU LRIT DC: ES2LRIT, THETIS, CSN, VMS PROXY (select just one option of the above) |
| Information about the Officer Responsible for the Server1 | Value |
| First Name |  |
| Last Name |  |
| E-mail 2 |  |
| Company Name |  |
| Registered Office Address |  |
| City/Town |  |
| Postal code |  |
| Province |  |
| Telephone |  |
| Fax |  |
| Requesting Organization Information | Value |
| Organization Name |  |
| Organization Unit 3 |  |
| Registered Office Address |  |
| City/Town |  |
| Postal code |  |
| Country |  |
| First Name of the Representative of the Organization4 |  |
| Last Name of the Representative of the Organization |  |
| E-mail of the Representative of the Organization5 |  |
| CSR Specific Information | Value |
| Common Name (CN) 6 |  |
| Revocation code 7 |  |
| Additional Information | Value |
| End-point 8 |  |
| Type of Server 9 |  |

1 The Officer Responsible for the Server is the operational reference person, authorized by the Representative of the Organization.

2 The electronic mailbox to which the Registration Form and the issued certificate are sent.

3 The Organization Unit of the web server is that which appears in the Organisational Unit (OU) in the subject field of the certificate.

4 The representative of the Organization is the person indicated by the appointment signed by the Legal Representative, or equivalent.

5 The electronic mailbox to which the Registration, which must be signed by the representative of the Organization or equivalent; the Appointment of the Officer Responsible for the Server and the issued certificate are sent.

6 The Fully Qualified Domain Name (FQDN) in case you are requesting a server certificate.

7 The revocation code is used to verify telephone requests. It consists of 9 numbers uniquely associated to the certificate requested.

8 The end-point is only needed for EU LRIT DC certificates (e.g.: https://es-evtest.member-state.eu/lrit2es, using SSL) and VMS PROXY certificates

9 The type of web server (IIS, ePlanet, Apache, etc.).

Place and date _______________________________

Signature of the Officer Responsible for the Server

# FORM C

# Appointment of officer responsible for the server

The undersigned, _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ , in his/her capacity as representative of the Organization/Authority named _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ designates Mr./Ms. _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ , as specified in the Certificate Registration Form application, as designated Officer Responsible for the Server in observance of the requirements related to the digital certification procedure.

Place and date _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _

Signature of representative and stamp of the Organization

ANNEX 3

      - Details Of F/Vs Participating To The Pilot Project

| ID | Flag | International Radio Call Sign (RC) | Vessel Name (NA) | External registration (XR) | IR number (IR) | AIS class (A, B) | MMSI | L.O.A. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |

Note: Details of 5 AIS equipped fishing vessels (a smaller number is also accepted) selected to participate in the pilot project.

2. Fishing areas assigned for the pilot project (in ESRI shape file format);

| No. | Fishing area | Description/ additional information |
| --- | --- | --- |
| 1. |  |  |

Note: Fishing areas, selected for the pilot project among those stated according to fishing regulations (preferably in ESRI shape file format).

3. List of users assigned for the pilot project;

| No. | Full Name | Organisation | Phone | Fax | e-mail | LoCode (if assigned) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |

Note: List of users planned to have access to the pilot project data, shall be provided to enable dealing with access rights management issues.

4. Examples of exchanged VMS messages (meaning the full string that generally encapsulates the NAF position message concerning both the position messages sent and received);